## Instructions
Quick Instructions
Start off in the "Projects" worksheet and enter the name for each project in column A.
Decide what default level of "tolerance" you will allow on the start and completion dates for the individual tasks. The "tolerance" is the number of days that a particular task can be "off plan" before it gets flagged as such in the status columns.
So, if the "tolerance" is set to 7, tasks will not be flagged as starting/ending early or being delayed or being late or completed if the actual start/completion date is within 7 days (plus or minus) of the planned date.
You can set the default tolerance to whatever you thing is appropriate. The default "tolerance" for specific tasks can be over-written manually in the "Tasks" worksheet.
The "Projects" worksheet acts as a top-level summary for all the projectes that your organisation has "on the go".
The information in the "Projects"sheet will be updated automatcially as you enter the detailed data for each project into the "Status" worksheet.
DO NOT ENTER ANYTHING into any of the other columns.
Even if initially they look empty, the cells there contain formulae which will calculate the information as data are entered into the "Tasks" worksheet.
Entering data into those "empty" cells will damage the worksheet which will then no longer work properly.
Then move to the "Tasks" worksheet.
In this worksheet you enter all the individual tasks that you have identified for each project, and the expected start and end/completion dates for those tasks.
Column A identifies the project of which the task is part. You select the appropriate project from the drop-down list which appears when you click on the cell. You can only choose projects which have already been set up in the "Projects" worksheet.
Column B is a description of the individual tasks. This is just "free text". (ie: anything you like).
Columns C & D are for the planned/scheduled start and expected completion dates that you have set for that particular task in your Master Project/Programme Plan.
Column E is the "tolerance" for that particular task. Initially it is whichever default "tolerance" your have set on the "Projects" worksheet. But you can over-write that manually by typing in anything else that you wish.
As you enter data into columns A-E (ie: as you set up a new project), if all the "Start" and "Completed" dates are in the future the status of those tasks will be automatically set to "Pending"
Columns F & G are for the actual start & completion dates for each task. Initially - ie: before the project starts - these will be left blank. But as the project gets under way you will be able to enter the dates that each task actually starts and is completed.
The actual Start & Completion dates can be either before, on or after the planned dates.
Columns H & I show the status of the individual task. The cells in these columns are calculated automatically from the data entered elsewhere.
It is important that you do not alter the formulae in these cells. If you do, the spreadsheet will no longer function correctly
As you enter data into the actual start & completion dates (columns F &G) the status of each task, shown in columns H & I will update automatically.
The summary status of the project (on the "Projects" worksheet) will also update automatically.
You'll see that on the righthand side of the heading cells (row 3) on the Tasks worksheet there is a dropdown arrow button. In case you are not familiar with that - it is a Filter button which allows you to select only those cells (and their associated rows) which contain the values checked in the dropdown tick boxes. So, for example, if you want to check for tasks which are past their start date but haven't been started you just click on the filter button and check just "Delayed" in the list.
You can filter on more than one column if you wish - so by also using the filter button in the "Project" you can select those tasks which are not yet started in particular projects (ie: rather than in all projects).
IMPORTANT NOTE: Worksheets with formulae in them are very susceptible to corruption (ie: the data "going all wrong") if you try to move cells/rows/columns around (because that can throw all the formulae "out of sync"). So if you decide that you want to move data (eg: add new rows; delete old rows, re-organise the data into a different order) it is better to use the "Sort" function rather than "click and drag" or "click and delete".
So, for example, if you want to insert a new task into the middle of existing tasks for a project - go to the first empty row in the Tasks worksheet and just type the new task in there.
Then go to the box at the left of the data entry line (below the menu bar) and using the dropdown button on the right of the cell, select "Tasks". That will highlight all the task cells in the worksheet. Then, in the menu bar of the "Data" tab select "Sort" and sort all the selected Task cells as required. Initially, until you are more familiar with sorting, I suggest that you select first on Column-A (project name), then on Column-C (expected start date) and then on Column-D (expected end date). That will sort all the tasks first into their projects, then by planned start-date and then (if more than one task starts on the same day) by their planned end date.
Once you are familiar with Sorting you will be able to achieve more things with it.
Copyright © 2019 Small Charity Support This spreadsheet is free-to-use and adapt by small charities and not-for-profit organisations. But its use and/or adaptation for any commercial purpose is not allowed.
Last updated 18-Aug-19

## Projects
Schedule of Projects | [7 empty] | Date Tolerance | 7
| Schedule |  | Actual |  | Status
Project | Start | Completion | Started | Completed | Start | Completion
Banani Centre | 2019-06-01 | 2019-08-03 | 2019-06-01 |  | Started | Delayed | WARNING! - Do not enter or delete data in ANY cells
Farmer Training Chittagong | 2018-04-01 | 2019-05-16 | 2018-04-01 | 2019-05-16 | Started | Completed | except K1 above, and the project names in column A
Matlab Water | 2019-04-01 | 2019-10-20 | 2019-04-04 |  | Started | Pending | All other cells are calculated automatically
For more projects, insert additional rows ABOVE this row
Formulas:
Schedule = IF([Project]="","",MINIFS(SchedStart,ProjectName,[Project]))
Completion = IF([Project]="","",MAXIFS(SchedEnd,ProjectName,[Project]))
Completion = IF([Project]="","",IF([Completed]="",IF([Completion]>TODAY(),"Pending","Delayed"),IF([Completed]<[Completion]-Tolerance,"Early",IF([Completed]<[Completion]+Tolerance,"Completed","Late"))))
Actual = IF([Project]="","",MINIFS(ActualStart,ProjectName,[Project]))
Status = IF([Project]="","",IF([Actual]="",IF([Schedule]>TODAY(),"Pending","Delayed"),IF([Actual]<[Schedule]-Tolerance,"Early",IF([Actual]<[Schedule]+Tolerance,"Started","Late"))))

## Tasks
Schedule of Projects & Tasks
|  | Schedule |  |  | Actual |  | Status |  | Warning! Do not enter or delete data in columns H & I
Project | Task | Start | Completion | Tol | Started | Completed | Start | Completion | The values in those cells are calculated automatically
Matlab Water | Site Survey | 2019-04-01 | 2019-04-10 | 3 | 2019-04-04 | 2019-04-05 | Started | Completed
Matlab Water | Quote from G&T | 2019-05-01 | 2019-05-10 | 2 | 2019-05-01 | 2019-05-06 | Started | Completed
Matlab Water | Final Budegt | 2019-05-13 | 2019-05-13 | 7 | 2019-05-13 | 2019-09-15 | Started | Late
Matlab Water | Final Proposal | 2019-05-20 | 2019-05-30 | 7 | 2019-05-13 | 2019-05-25 | Started | Completed
Matlab Water | Applicatiosns Submitted | 2019-06-01 | 2019-08-01 | 7 |  |  | Delayed | Delayed
Matlab Water | Contractor Confirmed (STF) | 2019-10-01 | 2019-10-01 | 7 |  |  | Pending | Pending
Matlab Water | Drilling | 2019-10-05 | 2019-10-15 | 2 |  |  | Pending | Pending
Matlab Water | Survey | 2019-10-16 | 2019-10-17 | 7 |  |  | Pending | Pending
Matlab Water | Drilling Report | 2019-10-17 | 2019-10-20 | 7 |  |  | Pending | Pending
Matlab Water | Revised quote from G&T | 2019-10-20 | 2019-10-20 | 7 |  |  | Pending | Pending
Farmer Training Chittagong | Organic Vegetable Training | 2018-04-01 | 2018-04-30 | 1 | 2018-04-01 | 2018-04-07 | Started | Early
Farmer Training Chittagong | Post harvest processes training | 2018-06-01 | 2018-06-10 | 3 | 2018-06-06 | 2018-06-12 | Started | Completed
Farmer Training Chittagong | Savings and Loans Training | 2018-06-01 | 2018-06-30 | 7 | 2018-06-05 | 2018-06-15 | Started | Early
Farmer Training Chittagong | Savings Group constitution | 2018-06-15 | 2018-07-15 | 7 | 2019-07-01 | 2018-07-07 | Late | Early
Farmer Training Chittagong | 1st Savings | 2018-08-01 | 2018-08-30 | 5 | 2018-08-25 | 2018-08-30 | Late | Completed
Farmer Training Chittagong | Livestock Training | 2018-09-01 | 2018-09-30 | 1 | 2018-09-01 | 2018-09-29 | Started | Completed
Farmer Training Chittagong | Loans Issued | 2018-10-05 | 2018-10-06 | 7 | 2018-10-06 | 2018-10-06 | Started | Completed
Farmer Training Chittagong | End of year data collection | 2019-02-01 | 2019-03-01 | 7 | 2019-02-01 | 2019-03-01 | Started | Completed
Farmer Training Chittagong | Nutrition Training | 2019-04-01 | 2019-04-07 | 7 | 2019-04-15 | 2019-04-17 | Late | Late
Farmer Training Chittagong | End of year report to funder | 2019-05-01 | 2019-05-16 | 7 | 2019-04-30 | 2019-05-16 | Started | Completed
Banani Centre | Community Meeting to launch | 2019-06-01 | 2019-06-02 | 7 | 2019-06-01 | 2019-06-02 | Started | Completed
Banani Centre | Collecting building materials | 2019-06-20 | 2019-06-30 | 0 | 2019-06-16 |  | Early | Delayed
Banani Centre | Digging Foundations (community) | 2019-06-24 | 2019-06-25 | 7 | 2019-06-24 | 2019-06-24 | Started | Completed
Banani Centre | Foundations built | 2019-07-01 | 2019-07-04 | 2 |  |  | Delayed | Delayed
Banani Centre | Walls Built to Head Height | 2019-07-06 | 2019-07-30 | 7 |  |  | Delayed | Delayed
Banani Centre | Lintel set | 2019-08-01 | 2019-08-03 | 7 |  |  | Delayed | Delayed
For more tasks, insert additional rows ABOVE this row
Formulas:
Status = IF([Task]="","",IF([Actual]="",IF([Schedule]>TODAY(),"Pending","Delayed"),IF([Actual]<[Schedule]-[Tol],"Early",IF([Actual]<[Schedule]+Tolerance,"Started","Late"))))
Completion = IF([Task]="","",IF([Completed]="",IF([Completion]>TODAY(),"Pending","Delayed"),IF([Completed]<[Completion]-Tolerance,"Early",IF([Completed]<[Completion]+[Tol],"Completed","Late"))))